## Status Tracker
Phase | Task | Owner | Target Date | Status | Notes
Requirements | Draft Business Requirements Document | Business/Operations Analyst | Week 1 | Done | BRD covers scope, stakeholders, functional requirements, and acceptance criteria
Requirements | Circulate BRD for stakeholder review | Business/Operations Analyst | Week 1 | Done | Reviewed by Operations, Client Relationship, and Compliance
Requirements | Stakeholder sign-off on requirements | All Stakeholders | Week 1 | Done | Approved by all three stakeholder groups
Data Setup | Build mock source dataset | Business/Operations Analyst | Week 2 | Done | 25 mock accounts, 23 active / 2 closed, generated with Faker
Build | Develop report generation pipeline | Business/Operations Analyst | Week 2 | Done | Python/Pandas pipeline built against FR-01 through FR-06
Build | Internal review of generated output | Business/Operations Analyst | Week 2 | Done | Spot-checked balances and account counts before UAT
UAT | Write UAT test cases | Business/Operations Analyst | Week 3 | Done | 10 test cases mapped to functional requirements and data quality scenarios
UAT | Execute UAT test cases | Business/Operations Analyst | Week 3 | Done | All 10 test cases passed; results logged in UAT_Test_Cases.xlsx
UAT | Log and resolve any defects | Business/Operations Analyst | Week 3 | Done | No defects found in this run
Sign-off | Final stakeholder review of tested report | All Stakeholders | Week 4 | Done | Report approved for use as the reference deliverable
Sign-off | Archive BRD, UAT results, and sample output | Business/Operations Analyst | Week 4 | Done | All artifacts stored in project repository